## Audit Report Draft
Audit Checklist
Planning
Sl No | Type | Checks | Applicability | Evidence | Availability | Location | Compliance | Correction | Root Cause | Corrective Action | Responsible | Status | Closure Date | Verified By | Remarks
1 | Planning | Are roles (e.g. PM, CM, BM) assigned to project members? | Applicable | PP (CM plan) | Available |  | Yes |  |  |  |  | Closed | 2023-02-06
2 | Planning | Is CM tool for repository and folder structure planned? | Applicable | PP (CM plan) (for tool), Project repository | Available |  | Yes |  |  |  |  | Closed | 2023-02-06
3 | Planning | Are configuration items identified for this project? | Applicable | PP (CM plan) | Not available |  | Yes |  |  |  |  | Open | 2023-02-06
4 | Planning | Is naming convention (for configuration items, folders in repository) defined? | Applicable | PP (CM plan) |  |  | No
5 | Planning | Are access rights to folders in repository planned for various CM roles? | Applicable | PP (CM plan) |  |  | No
6 | Planning | Is criteria for baselining defined (by stating in PP or referencing organizational/external documents)? | Applicable | PP (CM plan) |  |  | No
7 | Planning | Is branch and merge (in repository) strategy defined ? | Applicable | PP (CM plan)
8 | Planning | Is revision history approach for config. items defined (by stating or referencing organizational/ external documents in PP (CM plan))? | Applicable | PP (CM plan)
9 | Planning | Is configuration status reporting planned? | Applicable | PP (CM plan)
10 | Planning | Is data backup planned for securing project data? | Applicable | PP (CM plan)
Execution
Sl No | Type | Checks | Applicability | Evidence | Availability | Location | Compliance | Correction | Root Cause | Corrective Action | Responsible | Status | Closure Date | Verified By | Remarks
11 | Execution | Are CM roles assigned in CM tool to project members as specified in PP? | Applicable | Project repository
12 | Execution | Is the directory structure in repository same as specified in PP (CM plan)? | Applicable | Project repository
13 | Execution | Are CIs placed in folders of repository as specified in PP? | Applicable
14 | Execution | Are naming and version numbering conventions followed for CIs as defined in PP (CM plan)? | Applicable | PP (CM plan), Project repository
15 | Execution | Are access rights provided to project members as specified in PP (CM plan)? | Applicable | PP (CM plan)
16 | Execution | Is baselining procedure followed for baselining? | Applicable | Product Baseline Checklist
17 | Execution | Is commit message format followed during baselining? | Applicable | Commit logs (SVN, Bit bucket etc.)
18 | Execution | Is branch and merge strategy as defined in PP followed? | Applicable | Project repository
19 | Execution | Do the baselined artifacts include revision history as defined in PP (CM plan)? | Applicable | Baselined artifacts
20 | Execution | Are all re-baselining of artifacts against approved change requests? | Applicable | Revision history of artifacts (for CR reference), Change control record (in Redmine/Bitbucket/other)
21 | Execution | Is configuration status reported as defined in PP (CM plan)? | Applicable | MSR
22 | Execution | Is data backed up as planned? | Applicable | <To check with IT>
23 | Execution | Is backup-up data verified for integrity? | Applicable | <To check with IT>
24 | Execution | Is baselining of work products communicated to all stakeholders? | Applicable | E-mail
25 | Execution | Are previous configuration audit reports available with all findings tracked to closure? | Applicable | CM audit report, project repository